## Project Timeline
TSDIS SCOPING PROJECT - REVISED TIMELINE
Transport Sector Database and Information System ¦ Yanda Tec for Department of Transport
Activity | Aug 25 | Sep 25 | Oct 25 | Nov 25 | Dec 25 | Jan 26 | Feb 26 | Mar 26
PHASE 1: INCEPTION
Project Mobilization | ✓
Inception Report |  | ✓ Delivered
PHASE 2: CONSULTATIONS
Agency Consultations (7/11) | [5 empty] | 7 done
Remaining (DoT, DoWH, CASA, RTA) | [6 empty] | 4 agencies
DELIVERABLES
Interim Report (Original) |  |  |  | Due Nov
Interim Report (Revised) | [6 empty] | 15 Feb
Final Report (Original) | [5 empty] | Due 25 Jan
Final Report (Revised) | [7 empty] | ★ 22 Mar
CONTRACT PERIOD
Original Contract | [5 empty] | Ends 25 Jan
Extension Period (+8 weeks) | [6 empty] | Feb | to 22 Mar
LEGEND
Completed |  | In Progress |  | Overdue |  | Extension
STATUS SUMMARY
Agencies Completed: | 7 of 11 | Agencies Remaining: | 4 | Extension Requested: | 8 Weeks | Contract Status: | Expired
KEY DATES
Contract Start |  | 25 August 2025
Original End Date |  | 25 January 2026
Today |  | 25 January 2026
Secretary Meeting |  | 26 January 2026
Proposed Interim Report |  | 15 February 2026
Proposed Final Report |  | 22 March 2026
TSDIS Scoping Project ¦ Yanda Tec Limited ¦ Prepared for Secretary Meeting 26 January 2026